## Sprint 1
Description | First establish working instances of CE class and have it viewable on a Jframe instance
Task ID | FeatureID | Assigned To | Description | Status | Notes
| MainWin |  | Create a (MainWin) enviornment to work off of | Complete | We'll be using this to view the pictures from the Servant and CE Classes
| Database |  | Create a Database class | Complete | We'll be using this to hold the CE's and Servant's together, For now Focus on Containing the Ces
| CE |  | Create a CE class | Complete | Parameters are based off of UML
| LCE |  | Create an ArrayList<> to hold the CE's together | Complete | The list will be held in the Database Class
| LCE |  | Create a viewing area within MainWin to view icons of available CEs within the database | Complete
| LCE |  | Create a JDialog to view CE information from MainWin | Complete | Functionally it works; Will need to go back and try and format the view window
| ToolBar |  | Include Toolbar | In Progress | Goal is to have at least two buttons, that switches between displaying a lists of CE's and Servant database's
| AddCE |  | Opens a new Window to enter information to create an store a CE object | Complete | Opens up a new Dialog window for User to enter information
| About |  | Include About Dialog for toolbar icons(Help > About) | In Progress | These options will be added on a MenuBar in the MainWin
| Exit |  | Exit the Main Program(File > Quit or x window control) | Complete | These options will be added on a MenuBar in the MainWin

## Sprint 2
Description | First establish working instances of CE class and have it viewable on a Jframe instance
Task ID | FeatureID | Assigned To | Description | Status | Notes
| ToolBar |  | Include Toolbar | In Progress | Goal is to have at least two buttons, that switches between displaying a lists of CE's and Servant database's
| About |  | Include About Dialog for toolbar icons(Help > About) | In Progress | These options will be added on a MenuBar in the MainWin
| Save |  | Save database data into a separate file | Complete | Goal is to be able to retain data over the years
| Open |  | Open and load database data from a separate file | Complete | The opposite of the Save feature. Allows to load previous database data.
| EventEff |  | Implement some way to add Event specific effects for Ces
These functions are pertaining the CE portion of the database.
| Servant |  | I want to track parameters of a given Servant |  | Requires Enums for Servant Classes,
| Skill |  | Track a Servant's skills |  | Requires construction of a Skill Class, possible image parameter of Skill Icons
| Lservant |  | Keep a list of Servants |  | Requires a database class and an arrayList of Servants. Need to be able to add and access available servants
| AscMats |  | Keep track of Ascension Mats |  | Requires a separate class for Ascension Materials
| AppSkill |  | Keep track of Servant Append Skills |  | Possibly requires an ArrayList<Skill> class field for Servant
| PassSkill |  | Keep track of Servant Passive Skills
| ActSkill |  | Keep track of Servant Active Skills
| AddServant |  | Open a new window to enter Servant Information

## Product Backlog
Product Name: | FGO Servant Wiki
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a…. | I want to… | So that I can…. | Notes
MainWin |  |  |  |  | 1 | Complete |  | Display a main Window with Menu | Use the program more easily | Baseline MASS from CSE1325
Database |  |  |  |  | 1 | Inprogress |  | Keep track of Ces and Servant Classes |  | Create a Database class to hold the Servant and CE Classes together
CE |  | 1 |  |  | 1 | Complete |  | Track the Image and ID# of a CE | Keep track of available CE's | Requires CE images & ID#.
LCE |  |  |  |  | 1 | Complete |  | Keep a list of CE's | Keep track of available CE's | ArrayList<CE> parameter within the main Database Class
AddCE |  |  |  |  | 1 | Complete |  | Open a new window to enter CE Information | Add new Ces to existing database
ToolBar |  |  |  |  | 1 | Inprogress |  | Include Toolbar | Click Buttons for actions
About |  |  |  |  | 1 | Inprogress |  | Include About Dialog for toolbar icons(Help > About) | Avoid Legal trouble
Exit |  |  |  |  | 1 | Complete |  | Exit the Main Program(File > Quit or x window control) | Quit reliably
LoadF |  |  |  |  | 2 |  |  | Load Data from a specified File(File>Open) | Persist Data through the years
SaveF |  |  |  |  | 2 |  |  | Save Data to a specified File (File> SaveAs) | Persist Data through the years
New |  |  |  |  | 2 |  |  | Create new Database | Open Additional Database if needed | Unlikely to happen, but possible
EventEff |  |  |  |  | 2 |  |  | Implement some way to add Event specific effects for Ces | Add limited time effects for certain Ces
Servant |  | 1 |  |  | 2 |  |  | I want to track parameters of a given Servant | Keep track of Servants in Database | Requires Enums for Servant Classes,
Skill |  | 1 |  |  | 2 |  |  | Track a Servant's skills |  | Requires construction of a Skill Class, possible image parameter of Skill Icons
Lservant |  | 1 |  |  | 2 |  |  | Keep a list of Servants | See what Servants are available | Requires a database class and an arrayList of Servants. Need to be able to add and access available servants
AscMats |  | 1 |  |  | 2 |  |  | Keep track of Ascension Mats | Keep track of Ascension/Skill Enhancements | Requires a separate class for Ascension Materials
AppSkill |  | 1 |  |  | 2 |  |  | Keep track of Servant Append Skills |  | Possibly requires an ArrayList<Skill> class field for Servant
PassSkill |  | 1 |  |  | 2 |  |  | Keep track of Servant Passive Skills
ActSkill |  | 1 |  |  | 2 |  |  | Keep track of Servant Active Skills
AddServant | [7 empty] | Open a new window to enter Servant Information | Add new servants to existing database